Marella Morad

Sprint 1 Stage

Estimation Effort 1 – Task 61C

Table of Contents

Introduction:	2

Effort Estimations and Justification:	2

Design Phase:	2

Development Phase:	2

Integration Phase:	2

Testing and QA Phase:	3

Documentation and Review Phase:	3

Deployment Phase:	3

WBS for Member Management Web Pages	3

# Introduction:

Based on previous experience with web development, gained through several units at university and my role as a Frontend Developer at work, I have selected the task of developing "Member Management Web Pages" for Sprint 1. To ensure an accurate effort estimate, it is necessary to decompose this backlog item into smaller, more manageable components using the Activity based WBS. Since there are multiple stages involved in achieving the item's Definition of Done as outlined in our Project Proposal, I will consider these stages, including designing, consulting, developing functionalities, and testing, as integral parts of completing this item.

# Effort Estimations and Justification:

## Design Phase:

| Task | Estimation | Justification |
| --- | --- | --- |
| Design the UI for the Add New Member Page | 90 minutes | Designing the user interface could involve creating wireframes, mockups, and consulting with the product owner and the team to ensure it meets the requirements. This is a substantial task that may take up to 1.5 hours (the first page may take longer, but the second page will be based on the first one, so combined, they might take around 90 minutes). |
| Design the UI for the Edit/Delete Existing Member Page |  |  |

## Development Phase:

| Task | Estimation | Justification |
| --- | --- | --- |
| Develop the Add New Member page functionality | 90 minutes | Implementing the basic functionality of adding a new member, including form validation and error handling. |
| Develop the Edit/Delete Existing Member page functionality | 90 minutes | Implementing the functionality to edit existing member details, including deleting existing member records and form validation. |

## Integration Phase:

| Task | Estimation | Justification |
| --- | --- | --- |
| Connect the Add New Member and Edit/Delete Existing Member pages to the backend and database. | 30 minutes | Integrating the frontend with the backend and database for adding, editing, and deleting member records. This task does not require a lot of time as the API will already be set up. |

## Testing and QA Phase:

| Task | Estimation | Justification |
| --- | --- | --- |
| Test the Add New Member page and fix any issues | 90 minutes | Performing manual testing to ensure the pages function correctly, i.e., members can be added successfully, then edited or deleted, and all the changes are reflected in the relevant database table(s). |
| Test the Edit Existing Member page and fix any issues |  |  |

## Documentation and Review Phase:

| Task | Estimation | Justification |
| --- | --- | --- |
| Document the code and functionality | 30 minutes | Documenting the code and functionality for future reference and maintenance. |
| Review with the product owner and team (through a team Showcase) | 30 minutes | Reviewing the completed pages with the product owner and team to ensure they meet requirements and expectations. |

## Deployment Phase:

| Task | Estimation | Justification |
| --- | --- | --- |
| Deploy the pages to the production environment | 30 minutes | Deploying the pages is a relatively quick process once development and testing are complete. |

Total Estimation = 90+90+90+30+90+30+30+30 = 480 minutes = 8 hours

# WBS for Member Management Web Pages

Figure 1 WBS for Member Management Web Pages including the Time Estimations in Minutes