Marella Morad

Sprint 2 Stage

Estimation Effort 2 – Task 63C

Table of Contents

Introduction:	2

Estimations by Analogy:	2

Step 1: Finding a Similar Task:	2

Step 2: Analyse Similarity and Differences:	2

Similarities:	2

Differences:	2

Step 3: Estimate Effort for Similar Parts	2

Step 4: Estimate Effort for Differences	2

Step 5: Calculate the Total Effort:	3

Justification and Conclusion:	3

# Introduction:

In Sprint 2, I have undertaken the task of developing the “Product Management Web Pages”. This endeavour demands an accurate estimation of effort to ensure efficient project planning and successful delivery. To achieve this, I have decomposed the backlog item into its constituent components:

- Creating a Web Page for Searching and Viewing the List of Products.

- Creating a Web Page for Adding New Products.

- Creating a Web Page for Editing and Deleting Existing Products.

My choice of estimation technique for this task is “Estimating by Analogy”. This method has been selected based on the previous task I estimated and completed in Sprint 1, the “Member Management Web Pages” backlog item. The two tasks are very similar which inclined me to select the “Estimating by Analogy” method as it bases estimations by drawing comparisons with similar past projects or tasks. In this report, I will provide detailed information about the estimation process, its rationale, and the insights gained from experience, which together will facilitate a more accurate estimation of effort for the "Product Management Web Pages" in Sprint 2.

# Estimations by Analogy:

## Step 1: Finding a Similar Task:

As I mentioned earlier, I chose the estimations by analogy technique as I could base the efforts estimation of this task based on the “Member Management Web Pages” task that I completed in Sprint 1. Therefore, I will be using the “Member Management Web Pages” task for this comparison.

## Step 2: Analyse Similarity and Differences:

In this step, I will compare the “Product Management Web Pages” task with the past task (Member Management Web Pages) in terms of functionality, user interface complexity, integration requirements and any unique challenges.

### Similarities:

Both tasks involve designing and developing web pages with forms for managing data. i.e., search, view, add, edit, and delete data from the database. They share similarities in terms of functionality, development phases, and integration with the backend.

### Differences:

One of the main differences in the specific data being managed (products vs. members). This could result in some variations in data validation and processing requirements. For example, products will have a product image, price, stock level and some other product specific properties that were not relevant to members.

## Step 3: Estimate Effort for Similar Parts

In Sprint 1, I estimated 8 hours for the completion of the “Member Management Web Pages” task. In reality, it took me 9 hours to complete the task. Given the big similarity these two tasks have in common, I will estimate 6 hours for the completion of the “Product Management Web Pages” mainly because I can rely on the existing architecture when building the product specific pages, which will largely reduce my efforts.

## Step 4: Estimate Effort for Differences

The primary distinction between members and products lies in our desire to incorporate an image for each product, not only to enhance visualization but also to align with industry standards. In order to accommodate image display and retrieval on the new web pages, I would estimate an additional hour of work. I am confident that allocating one hour for this modification is adequate, drawing from my previous experience with integrating images into web pages.

## Step 5: Calculate the Total Effort:

Summing up the efforts of similarities and differences adds up to a total of 7 hours (420 minutes).

# Justification and Conclusion:

The "Estimating by Analogy" technique was employed to estimate the effort required for the current task, which involves the development of Products Management Web Pages, based on its similarity to a previous task involving Member Management Web Pages. Upon close analysis, it became evident that these two tasks share numerous similarities, especially in terms of development phases and functionality.

One significant advantage that influenced the estimation was the fact that the previous task was executed within the same project. This provided a valuable head start for the current task by offering existing templates and architectural foundations for the new web pages. As a result, the estimation for the common elements was reduced to 6 hours.

In regard to the different properties, the primary change involves the incorporation of image support, a feature not present in the previous task. This additional functionality is estimated to require an extra hour of effort. Consequently, the total estimated time for the completion of the "Products Management Web Pages" is 7 hours.

I have confidence in this estimation, given the thorough analysis of similarities and differences between the two tasks. I believe that the allocated 7 hours represent a realistic timeframe for the successful completion of this task.