## Sheet1
Feature | Backlog ID | JIRA ID | Initial Estimate | 4/09/2023 | 5-Sep | 6-Sep | 7-Sep | 8-Sep | 18-Sep | 19-Sep | 20-Sep | 21-Sep | 22-Sep | Points Left
Create database table for members | F01 | MCT-7 | 3 | 2 | [9 empty] | 0 | Effort | bar: 5-Sep
Create database table for sales | F02 | MCT-8 | 3 | 2 | [9 empty] | 0 | Dev | Testing | bar: 5-Sep
Create database table for products | F03 | MCT-9 | 3 | 2 | [9 empty] | 0 | bar: 5-Sep
Create endpoint for adding members | F04 | MCT-11 | 3 | [10 empty] | 1 | bar: 6-Sep to 7-Sep
Create endpoint for editing members | F05 | MCT-12 | 3 | [10 empty] | 1 | bar: 6-Sep to 7-Sep
Create endpoint for removing members | F06 | MCT-13 | 3 | [10 empty] | 1 | bar: 6-Sep to 7-Sep
Create endpoint for adding sales records | F07 | MCT-14 | 3 | [10 empty] | 1 | bar: 7-Sep to 8-Sep
Create endpoint for editing sales records | F08 | MCT-15 | 3 | [10 empty] | 1 | bar: 7-Sep to 8-Sep
Create endpoint for removing sales records | F09 | MCT-16 | 3 | [10 empty] | 1 | bar: 7-Sep to 8-Sep
Create endpoint for adding products | F10 | MCT-18 | 3 | [10 empty] | 1 | bar: 8-Sep to 18-Sep
Create endpoint for editing products | F11 | MCT-19 | 3 | [10 empty] | 1 | bar: 8-Sep to 18-Sep
Create endpoint for removing products | F12 | MCT-20 | 3 | [10 empty] | 1 | bar: 8-Sep to 18-Sep
Create endpoint for retrieving products | F13 | MCT-21 | 3 | [10 empty] | 1 | bar: 5-Sep to 6-Sep
Create endpoint for retrieving sales records | F14 | MCT-48 | 3 | [10 empty] | 1 | bar: 5-Sep to 6-Sep
Create endpoint for retrieving members | F15 | MCT-47 | 3 | [10 empty] | 1 | bar: 5-Sep to 6-Sep
Generate Sales Reports | F17 | MCT-24 | 8 |  | 19-Sep: 2; 20-Sep: 2; 21-Sep: 3; 22-Sep: 1 | 0
Generate Inventory Reports | F17 | MCT-42 | 8 |  | 19-Sep: 2; 20-Sep: 2; 21-Sep: 3; 22-Sep: 1 | 0
User Authentication and account management | F18 | MCT-26 | 8 |  | 7-Sep: 4; 8-Sep: 3; 19-Sep: 2 | -1
Build web page to allow users to add new Members | F19 | MCT-27 | 5 |  | 8-Sep: 4; 20-Sep: 2 | -1
Build web page to allow users to edit/delete existing members | F20 | MCT-28 | 5 |  | 18-Sep: 4; 21-Sep: 2 | -1
|  | Setting | Start | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Average
|  | Planned Hours |  | 7.9 | 7.9 | 7.9 | 7.9 | 7.9 | 7.9 | 7.9 | 7.9 | 7.9 | 7.9 | 7.9
|  | Actual Hours |  | 6 | 6 | 6 | 10 | 13 | 7 | 6 | 6 | 8 | 2 | 7
|  | Remaining Effort | 79 | 73 | 67 | 61 | 51 | 38 | 31 | 25 | 19 | 11 | 9
|  | Ideal Burndown | 79 | 71.1 | 63.2 | 55.3 | 47.4 | 39.5 | 31.6 | 23.7 | 15.8 | 7.9 | 0